## Sheet1
Column1 | OCT | NOV | DEC | IAN | FEB
Project Setup
- Assemble Team
- Define Project
- Create Requirements Document
- Create Use Case Diagram
- Define User Stories
- Estimate User Stories
1/3 of Backlog Implemented
- Create Sprint Backlog
- Create Project Workflow diagram
- Create Database diagram
- Create UML Use Case diagram
- Create Gantt Diagram
- Implement 1/3 of Backlog
-> Add User Authentication System
-> Add Ability to post questions
-> Improve question browsing navigation |  | Dependency: ability to post questions
-> Add Ability to answer questions |  | Dependency: ability to post questions
-> Add Ability to edit questions |  | Dependency: ability to post questions
-> Add Ability to delete questions |  | Dependency: ability to post questions
-> Add Admin privileges |  | Dependency: ability to delete questions
2/3 of Backlog Implemented
3/3 of Backlog Implemented